## Projections & Estimates
Projections and Estimates
| 1 | 4 | 1 | Weighting
High Level Tasks | Most Pessimistic | Most Likely | Most Optimistic | Pert Estimation |  | Tasks >= 100
High Level Design | 64 | 36 | 32 | 40 |  | 3
Technical Design | 160 | 115 | 100 | 120
Development | 760 | 575 | 480 | 590
Unit Testing | 100 | 70 | 40 | 70 |  | 240
Integrated Testing | 110 | 80 | 50 | 80 |  | 240
User Acceptance Testing | 130 | 110 | 30 | 100
TOTAL HOURS |  |  |  | 1000
Estimated Fixed Expenses |  |  | Expenses
5% |  |  | Previous Fixed Expenses | 92000
6.5% |  |  | Estimated Increase | 9%
8%
9.5%
11% |  |  | Sales
12.5% |  |  | Sale Price | 35
14% |  |  | Previous Sales Units | 4700
15.5% |  |  | Expected Increase | 7%
Estimated Income
| 30 | 32.5 | 35 | 37.5 | 40 | 42.5 | 45
3%
4%
5%
6%
8%
9%
10%
11%

## Project Costing Model
Project Costing Overview
Project Variables |  | Project Duration
Software Manuals | 10 | Total effort (hours) | 10000
Man Hours per Manual | 1000 | Total working week (hours) | 400
Total staff | 10 | Calculated duration (weeks) | 25
Working day (hours) | 8
Working week (days) | 5 | Salary calculations (per person per week)
Standard Work Week Hours | 35 | Total hours per week | 40
Standard Hourly Rate | 50 | Base salary ($50 per hour up to 40 hours per week) | 2000
Overtime Hourly Rate | 75 | Overtime salary ($75 per hour over 40 hours per week) | 375
Costs |  | Revenues
Weekly salary (per person) | 2375 | Sale Price | 35
Total weekly salaries | 23750 | Quantity Sold (Per Manual) | 2140
Total project salaries | 593750 | Per Manual Revenue | 74900
Fixed Overheads | 100000 | Total Revenue | 749000
Total Project Costs | 693750 | Projected Profit | 55250